## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a researcher, I want to gather information about the traditional IVR System. | Should Have | Dataset availability | Backend Team | Completed
Sprint 2 | Sprint 2 | US002 | As a Backend Developer, I want to make some Basic APIs for the traditional IVR System. | Should Have | APIs ready | Backend Team | Completed
Sprint 3 | Sprint 3 | US003 | As an AI developer, I want to integrate an AI layer in the traditional IVR System to make it a AI Conversational IVR System with the help of Machine Learning and NLU. | Must Have | APIs ready | Backend Team | Completed
Sprint 3 | Sprint 3 | US003 | As an AI developer, I want to integrate NLU, STT, intent detection, entity extraction, Data Flow management system, TTS | Must Have | APIs ready | Backend Team | Completed
Sprint 4 | Sprint 4 | US004 | As a frontend developer, I want to create an interactive User Interface of our system for the users so that they can use and interact with the system efficiently without any issues. | Must Have | User Interface | Frontend Team | Completed
Sprint 4 | Sprint 4 | US005 | As a DevOps engineer, I want to deploy and integrate the entire system in a test environment for demonstration. | Could Have | Backend & frontend integration | Both Teams | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US001 | T1 | Gathered all the information of the Traditional IVR System | 2026-02-06 | 2026-02-07 | Documentation1 | Data Collection | Done | 6 | bar: Day 1 to Day 2
US001 | T2 | Documented all the information in a word file with proper achitecture and use cases | 2026-02-09 | 2026-02-10 | Documentation2 | Data Collection | Done | 5 | bar: Day 2 to Day 4
US002 | T3 | Made Some basic API endpoints for the traditional IVR System | 2026-02-22 | 2025-02-28 | Backend1 | Model Training | Done | 6 | bar: Day 3 to Day 4
US003 | T4 | Integrated the AI layer in the System | 2026-03-03 | 2026-03-06 | Backend2 | AI Integration | Done | 10 | bar: Day 4 to Day 7
US003 | T5 | Implemented NLU, STT, intent detection in the system | 2026-03-07 | 2026-03-11 | Backend3 | AI Integration | Done | 12 | bar: Day 6 to Day 9
US003 | T6 | Implemented entity extraction, data flow, TTS in the system | 2026-03-12 | 2026-03-14 | Backend4 | AI Integration | Done | 5 | bar: Day 7 to Day 10
US004 | T7 | Implemented User Interface for the better experience | 2026-03-18 | 2026-03-24 | FrontEnd1 | Web Dev | Done | 5 | bar: Day 9 to Day 11
US005 | T8 | Tested some edge cases and deployed the system | 2026-03-25 | 2026-03-28 | Both Teams | Deployment | Done | 5 | bar: Day 12 to Day 14
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | None | drafting the system design of the project
Sprint 1 | Day 2 | None | created base structure of the backend
Sprint 2 | Day 3 | testing api end points | Creating api endpoints
Sprint 2 | Day 4 | testing api end points | Creating api endpoints
Sprint 3 | Day 5 | addition of AI layer | Stress tested and added security
Sprint 3 | Day 6 | entity tracking and endpoint checking | created STT and TTS modules
Sprint 3 | Day 7 | managing session management | entity tracking and endpoint checking
Sprint 3 | Day 8 | testing session management and enabling cloud based database module | added session management
Sprint 4 | Day 11 | migrating to supabase | tested session management
Sprint 4 | Day 12 | testing the project end to end | migrated to supabase
Sprint 4 | Day 13 | deployment of the project | stress tested the entire project
Sprint 4 | Day 14 | None | Deployed the application in vercel

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-02-03 | 2026-02-16 | Harsha sri | Drafting the system design of the application | Starting development without a documented system design | Extending AI Hospital IVR Web Simulator capabilities | drafting the system design of the application
2 | 2 | 2026-02-18 | 2026-02-28 | Harsha sri | Setting up proper backend architecture and folder structure | Jumping into coding without establishing base structure | Building and documenting the backend foundation | created base structure of the backend
3 | 2 | 2026-02-18 | 2026-02-28 | Harsha sri | Writing automated tests for each API endpoint before merging | Creating API endpoints without test coverage | REST API development and code reviews | Creating api endpoints testing api end points
4 | 2 | 2026-02-18 | 2026-02-28 | Harsha sri | Adding request/response validation on all endpoints | Skipping input validation on existing API endpoints | REST API development and code reviews | Creating api endpoints testing api end points
5 | 3 | 2026-03-04 | 2026-03-14 | Harsha sri | Implementing component-based and responsive UI architecture | Writing monolithic JavaScript for frontend without modularity | Iterative UI improvements based on user feedback | created the base UI using js improvement in the frontend UI
6 | 3 | 2026-03-04 | 2026-03-14 | Harsha sri | Using reusable UI components to speed up development | Rewriting similar UI sections without reusable components | Iterative UI improvements based on user feedback | improved the UI improvement in the frontend UI
7 | 3 | 2026-03-04 | 2026-03-14 | Harsha sri | Integrating AI layer (STT/TTS) with proper validation and fallback | Delaying security testing to the end of the sprint | Stress testing and security hardening across all modules | Stress tested and added security addition of AI layer addition security and stress testing
8 | 3 | 2026-03-04 | 2026-03-14 | Harsha sri | Testing STT/TTS modules in isolation before full integration | Merging AI modules without unit-level testing | Stress testing and security hardening across all modules | created STT and TTS modules addition of AI layer
9 | 4 | 2026-03-18 | 2026-03-28 | Harsha sri | Centralised cloud-based session management from the start | Using in-memory / stateless session tracking approach | Entity tracking and endpoint health monitoring | entity tracking and endpoint checking managing session management
10 | 4 | 2026-03-18 | 2026-03-28 | Harsha sri | Enabling cloud-based database module early in the sprint | Deferring cloud database migration until last steps | Entity tracking and endpoint health monitoring | added session management testing session management and enabling cloud based database module
11 | 4 | 2026-03-18 | 2026-03-28 | Harsha sri | Adopting cloud-first database strategy using Supabase for all modules | Maintaining local/in-memory database implementations | Testing session management workflows post-migration | tested session management migrating to supabase
12 | 4 | 2026-03-18 | 2026-03-28 | Harsha sri | Running regression tests immediately after each migration step | Migrating all data without incremental testing checkpoints | Testing session management workflows post-migration | migrated to supabase testing the project end to end
13 | 4 | 2026-03-18 | 2026-03-28 | Harsha sri | Setting up CI/CD pipeline for automated builds and deployments | Manual deployment processes and ad-hoc testing | End-to-end testing and full system stress testing | stress tested the entire project deployment of the project testing the project end to end
14 | 4 | 2026-03-18 | 2026-03-28 | Harsha sri | Documenting deployment steps and post-deployment monitoring | Deploying without post-deployment health checks | End-to-end testing and full system stress testing | Deployed the application in vercel deployment of the project